## TWAP FSP WP - 2 years
ANNEX 1: WORK PLAN 2012
WORK PLAN
Appendix 5 : Work plan and timetable
Components/Sub-components/Activities/Sub-activities |  | 2013 | [11 empty] | 2014 | [11 empty] | Responsible entity
|  | I | II | III | IV | V | VI | VII | VIII | IX | X | XI | XII | I | II | III | IV | V | VI | VII | VIII | IX | X | XI | XII
Component I: A Global Comparative Baseline Assessment of Transboundary Aquifers (TBAs) and SIDS Groundwater Systems
Sub-component I.1: Assessment of TBAs and SIDS groundwater systems
Activity I.1.1: Data and Information Gathering
Sub-activity 1: For major TBAs | [25 empty] | UNESCO-IHP and IGRAC (with core group, regional and technical partners) | bar: IX to XII
Sub-activity 2: For SIDS groundwater systems | [25 empty] | As above in Sub-activity 1
Sub-activity 3: Modeling and remote sensing | [25 empty] | University of Frankfurt, IGRAC | bar: IX to 2014 IV
Activity I.1.2: Assessment of TBAs and SIDS groundwater systems
Sub-activity 1: Assessment of TBAs | [25 empty] | As above is Sub-activity 1
Sub-activity 2: Assessment of SIDS groundwater systems | [25 empty] | As above is Sub-activity 1
Sub-activity 3: Determine priority aquifers/regions | [25 empty] | UNESCO-IHP and IGRAC
Sub-activity 4: Outlook projections for 2030 and 2050 | [25 empty] | University of Frankfurt, IGRAC | bar: 2014 V to 2014 VII
Activity I.1.3: Assessment Reporting
Sub-activity 1: Comprehensive Report on major issues for TBAs & SIDS | [21 empty] | X |  |  | X | UNESCO-IHP and IGRAC | bar: 2014 VI to 2014 VII
Activity I.1.4: Data and Information Management | [25 empty] | IGRAC
Sub-component I.2: Sustainability of the TBA assessment
Activity I.2.1: Establishment of a periodic assessment system
Sub-activity 1: Sustainability of consortium of partners | [25 empty] | UNESCO-IHP and IGRAC | bar: IX; XI; 2014 I; 2014 III; 2014 V; 2014 VII
Sub-activity 2: Sustainability of the assessment process | [25 empty] | UNESCO-IHP, WWAP and IGRAC | bar: IX; XI; 2014 I; 2014 III; 2014 V; 2014 VII
Sub-activity 3: Sustainability of the TBA data and information management system | [25 empty] | IGRAC
Sub-component I.3: Assessment Coordination
Activity I.3.1 Coordination of the assessment process | [25 empty] | UNESCO-IHP
x Delivery of outputs
Component II: A Global Comparative Baseline Assessment of Transboundary Lake Basins and Lake Basins at Risk
Sub-component II.1: Assessment of Lake Basins
Activity II.1.1: Data and Information gathering
Sub-activity 1: For transboundary lake basins | [25 empty] | ILEC
Sub-activity 2: For lake basins at risk | [25 empty] | ILEC/TSU | bar: IX
Sub-activity 3: For linked lentic and lotic water systems | [25 empty] | ILEC/TSU
Activity II.1.2: Transboundary Lake Basins assessment
Sub-activity 1: Assessment for transboundary lake basins | [25 empty] | ILEC
Sub-activity 2: Assessment for lake basins at risk | [25 empty] | ILEC | bar: IX to XII
Sub-activity 3: Assessment for linked lentic and lotic water systems | [25 empty] | ILEC
Sub-activity 4: Assessment of cross-cutting issues (socioeconomic issues, governance) | [25 empty] | ILEC | bar: X to 2014 VI
Sub-activity 5: Validation process | [25 empty] | ILEC
Sub-activity 6: Determine priority Lake Basins/regions | [25 empty] | ILEC | bar: IX to 2014 V
Sub-activity 7: Outlook projections for 2030 and 2050 | [25 empty] | ILEC
Activity II.1.3: Assessment Reporting
Sub-activity 1: Report on major issues for transboundary lake basins and lakes at risk + linked lentic and lotic water systems | [25 empty] | ILEC/TSU | bar: IX to X
Sub-activity 2: Report on priority transboundary lake basins and lakes at risk + linked lentic and lotic water systems | [25 empty] | ILEC/TSU
Sub-activity 3: Report on needed responses | [25 empty] | ILEC/TSU | bar: 2014 VI to 2014 VII
Sub-component II.2: Sustainability of the Transboundary Lake Basins Assessment
Activity II.2.1: Establishment of a periodic assessment system
Sub-activity 1: Sustainability of consortium of partners | [25 empty] | ILEC | bar: 2014 I to 2014 VI
Sub-activity 2: Sustainability of the assessment process - an evaluation framework to identify high risks transboundary lake basins | [25 empty] | ILEC | bar: 2014 VI to 2014 VII
Sub-activity 3: Data and information management system | [25 empty] | ILEC/TSU
Sub-component II.3: Assessment Coordination
Activity II.3.1: Lake sub-project management | [25 empty] | ILEC/TSU
Component III: A Global Comparative Baseline Assessment of Transboundary River Basins
Sub-component III.1: Water quantity & quality | [25 empty] | UDC*
Activity III.1.1: Environmental water stress - current | [25 empty] | CESR*
Sub-activity 1: Standardise data | [25 empty] | CESR
Sub-activity 2: Preliminary analysis | [7 empty] | X | [17 empty] | CESR
Sub-activity 3: Detailed analysis | [20 empty] | X |  |  |  |  | CESR
Activity III.1.2: Environmental water stress - projected | [25 empty] | CESR*
Sub-activity 1: Analysis | [20 empty] | X |  |  |  |  | CESR | bar: 2014 III to 2014 VII
Activity III.1.3: Agricultural water stress | [25 empty] | CESR*
Sub-activity 1: Standardise data | [25 empty] | CESR
Sub-activity 2: Preliminary analysis | [7 empty] | X | [17 empty] | CESR
Sub-activity 3: Detailed analysis | [20 empty] | X |  |  |  |  | CESR
Activity III.1.4: Urban water quality | [25 empty] | UDC*
Sub-activity 1: Standardise data | [25 empty] | CESR
Sub-activity 2: Preliminary analysis | [7 empty] | X | [17 empty] | UDC
Sub-activity 3: Detailed analysis | [20 empty] | X |  |  |  |  | UDC
Activity III.1.5: Lake influence | [25 empty] | CESR*
Sub-activity 1: Standardise dataset with Lakes component | [25 empty] | CESR | bar: 2014 IV
Sub-activity 2: Calculate 'lake influence' on river basins | [20 empty] | X |  |  |  |  | CESR | bar: 2014 V to 2014 VII
Activity III.1.6: Human water stress - current | [25 empty] | CUNY*
Sub-activity 1: Standardise data | [25 empty] | CUNY
Sub-activity 2: Preliminary analysis | [7 empty] | X | [17 empty] | CUNY
Sub-activity 3: Detailed analysis | [20 empty] | X |  |  |  |  | CUNY
Activity III.1.7: Human water stress - projected | [25 empty] | CUNY*
Sub-activity 1: Analysis | [20 empty] | X |  |  |  |  | CUNY | bar: 2014 III to 2014 VII
Activity III.1.8: Nutrients - current | [25 empty] | IGBP*
Sub-activity 1: Standardise data | [25 empty] | IGBP
Sub-activity 2: Preliminary analysis | [7 empty] | X | [17 empty] | IGBP
Sub-activity 3: Detailed analysis | [20 empty] | X |  |  |  |  | IGBP
Activity III.1.9: Nutrients - projected | [25 empty] | IGBP*
Sub-activity 1: Analysis | [20 empty] | X |  |  |  |  | IGBP | bar: 2014 III to 2014 VII
Activity III.1.10: Water quantity & quality reporting | [25 empty] | CESR*
Sub-activity 1: Reporting | [8 empty] | X | [13 empty] | X |  |  | CESR/CUNY/IGBP/UDC | bar: 2014 VII
Sub-components III.2: Ecosystems | [25 empty] | IUCN*
Activity III.2.1: Biodiversity & habitat loss | [25 empty] | IUCN*
Sub-activity 1: Standardise data (wetland disconnectivity) | [25 empty] | CUNY
Sub-activity 2: Preliminary analysis with Red List data | [7 empty] | X | [17 empty] | IUCN
Sub-activity 3: Detailed analysis | [20 empty] | X |  |  |  |  | IUCN
Activity III.2.2: Ecosystem integrity | [25 empty] | CUNY*
Sub-activity 1: Standardise data | [25 empty] | CUNY
Sub-activity 2: Preliminary analysis | [7 empty] | X | [17 empty] | CUNY
Sub-activity 3: Detailed analysis | [20 empty] | X |  |  |  |  | CUNY
Activity III.2.3: Fish threat | [25 empty] | CUNY*
Sub-activity 1: Standardise data | [25 empty] | CUNY
Sub-activity 2: Preliminary analysis | [7 empty] | X | [17 empty] | CUNY
Sub-activity 3: Detailed analysis | [20 empty] | X |  |  |  |  | CUNY
Activity III.2.4: Ecosystems reporting | [25 empty] | IUCN*
Sub-activity 1: Reporting | [8 empty] | X | [13 empty] | X |  |  | IUCN/CUNY | bar: 2014 VII
Sub-components III.3: Governance | [25 empty] | SIWI*
Activity III.3.1: Governance architecture | [25 empty] | SIWI*
Sub-activity 1: Questionnaire design | [25 empty] | SIWI
Sub-activity 2: Questionnaire distribution & completion | [25 empty] | SIWI | bar: IX to XII
Sub-activity 3: Analysis | [20 empty] | X |  |  |  |  | SIWI | bar: IX; 2014 I to 2014 VII
Activity III.3.2: Institutional resilience - current | [25 empty] | OSU*
Sub-activity 1: Analysis | [8 empty] | X | [11 empty] | X |  |  |  |  | OSU | bar: 2014 II to 2014 VII
Activity III.3.3: Institutional resilience - projected | [25 empty] | OSU*
Sub-activity 1: Analysis | [20 empty] | X |  |  |  |  | OSU | bar: 2014 II to 2014 VII
Activity III.3.4: Enabling environment | [25 empty] | UDC*
Sub-activity 1: Analysis | [8 empty] | X | [11 empty] | X |  |  |  |  | UDC | bar: 2014 II to 2014 VII
Activity III.3.5: Governance reporting | [25 empty] | SIWI*
Sub-activity 1: Reporting | [8 empty] | X | [13 empty] | X |  |  | SIWI/OSU/UDC | bar: 2014 VII
Sub-components III.4: Socioeconomics | [25 empty] | SIWI*
Activity III.4.1: Economic dependence on water resources | [25 empty] | CIESIN*
Sub-activity 1: Standardise data | [25 empty] | CIESIN
Sub-activity 2: Preliminary analysis | [7 empty] | X | [17 empty] | CIESIN
Sub-activity 3: Detailed analysis | [20 empty] | X |  |  |  |  | CIESIN
Activity III.4.2: Societal well-being | [25 empty] | CIESIN*
Sub-activity 1: Standardise data | [25 empty] | CIESIN
Sub-activity 2: Preliminary analysis | [7 empty] | X | [17 empty] | CIESIN
Sub-activity 3: Detailed analysis | [20 empty] | X |  |  |  |  | CIESIN
Activity III.4.3: Vulnerability to climate-related natural disasters | [25 empty] | CIESIN*
Sub-activity 1: Standardise data | [25 empty] | CIESIN
Sub-activity 2: Preliminary analysis | [7 empty] | X | [17 empty] | CIESIN
Sub-activity 3: Detailed analysis | [20 empty] | X |  |  |  |  | CIESIN
Activity III.4.4: Population density - projected | [25 empty] | CIESIN*
Sub-activity 1: Analysis | [20 empty] | X |  |  |  |  | CIESIN | bar: 2014 II to 2014 VII
Activity III.4.5: Socioeconomics reporting
Sub-activity 1: Reporting | [8 empty] | X | [13 empty] | X | bar: 2014 VII
Sub-components III.5: Deltas | [25 empty] | DA
Activity III.5.1: Deltas assessment | [25 empty] | DA
Sub-activity 1: Analysis | [7 empty] | X | [12 empty] | X |  |  |  |  | DA | bar: 2014 II to 2014 VII
Activity III.5.2: Deltas reporting | [25 empty] | DA
Sub-activity 1: Reporting | [8 empty] | X | [13 empty] | X |  |  | DA
Sub-component III.6: Analysis & reporting | [25 empty] | UDC*
Activity III.6.1: River basin factheets | [25 empty] | UDC*
| Sub-activity 1: Create factsheets | [19 empty] | X |  |  |  |  | UDC | bar: IX to X; 2014 III to 2014 VII
Activity III.6.2: Data & information management | [25 empty] | UDC*
Sub-activity 1: Ensure compatibility with data sources & TWAP portal (subject to coordination with Component VII) | [25 empty] | UDC | bar: 2014 II to 2014 III
Sub-activity 2: Establish website (demo version June 2014, final Dec. 2014) | [24 empty] | X | UDC | bar: IX; 2014 III to 2014 VI
Activity III.6.3: Cross-cutting analysis (Subject to coordination with Component VI) | [25 empty] | UDC
Sub-activity 1: Participate in common governance assessment | [25 empty] | SIWI
Sub-activity 2: Participate in common socioeconomic assessment | [25 empty] | CIESIN
Activity III.6.4: Integrated assessment | [25 empty] | UDC
Sub-activity 1: Group meetings | [21 empty] | X |  |  |  | UDC | bar: IX
Sub-activity 2: Create indices | [25 empty] | UDC
Sub-activity 3: Create maps & reports (online) | [25 empty] | UDC | bar: IX
Sub-activity 4: Global assessment report (electronic) | [24 empty] | X | UDC | bar: IX
Sub-component III.7: Sustainability | [25 empty] | SIWI
Activity III.7.1: Design and establish periodic assessment framework | [25 empty] | SIWI
Sub-activity 1: Sustainability of consortium of partners | [25 empty] | SIWI | bar: IX; 2014 VII
Sub-activity 2: Sustainability of the assessment process | [25 empty] | SIWI | bar: IX; 2014 VII
Sub-activity 3: Data and information management system | [25 empty] | SIWI | bar: IX; 2014 VII
Sub-component III.8: Component coordination | [25 empty] | UDC
Activity III.8.1: Contract management |  |  | X | [22 empty] | UDC
Activity III.8.2: Meeting arrangement |  | X | [23 empty] | SIWI | bar: IX
Activity III.8.3: Component communication | [25 empty] | UDC
Activity III.8.4: Progress / financial reporting | [7 empty] | X | [16 empty] | X | UDC | bar: XII to 2014 I; 2014 VI to 2014 VII
* Responsible entity for 'sub-components' and 'activities' indicate the coordinating entity for that sub-component or activity. x Delivery of outputs
Component IV: Global Comparative Baseline Assessment of LMEs
Sub-component IV.1: Assessment of LMEs and the Pacific warm pool
Activity IV.1.1 : Thematic assessments
Sub-Activity IV.1.1.1 Habitats | [20 empty] | X |  |  |  |  | UNEP-WCMC | bar: IX to 2014 VII
Sub-Activity IV.1.1.2 Pollution | [20 empty] | X |  |  |  |  | GESAMP | bar: IX to 2014 VII
Sub-Activity IV.1.1.3 Fisheries | [20 empty] | X |  |  |  |  | UBC | bar: IX to 2014 VII
Sub-Activity IV.1.1.4 Nutrients | [20 empty] | X |  |  |  |  | IGBP | bar: IX to 2014 VII
Sub-Activity IV.1.1.5 Productivity/SST | [20 empty] | X |  |  |  |  | NOAA/URI | bar: IX to 2014 VII
Sub-Activity IV.1.1.6 Socioeconomics | [20 empty] | X |  |  |  |  | Consultant | bar: IX to 2014 VII
Sub-Activity IV.1.1.7 Governance | [20 empty] | X |  |  |  |  | CERMES | bar: IX to 2014 VII
Sub-Activity IV.1.1.8 Cumulative Mapping/OHI | [20 empty] | X |  |  |  |  | CMAP | bar: IX to 2014 VII
Sub-Activity IV.1.1.9 Ranking of LMES | [21 empty] | X |  |  |  | Working Group | bar: 2014 VI to 2014 VII
Sub-Activity IV.1.1.10 Pilot Level 2 assessment- Bay of Bengal LME | [20 empty] | X |  |  |  |  | IOC/BOB LME project
Activity IV.1.2 Preparation of assessment products
Sub-Activity IV.1.2.1: Validation and peer review | [22 empty] | x |  |  | IOC | bar: 2014 VII
Sub-Activity IV.1.2.2: TWAP LME Assessment report | [24 empty] | x | Working Group/IOC | bar: IX
Sub-component IV.2: Sustainability of LME assessment
Activity IV.2.1: Establishment of a sustainable consortium of partners
Sub-activity IV.2.1.1: Working Group Coordination (Meetings) |  |  | X | [22 empty] | IOC | bar: IX to 2014 VII
Activity IV.2.2: Development of a framework for sustainability of the assessment process
Sub-activity IV.2.2.1: Participation in stakeholders meetings (RS, RP, LME meetings, etc) | [25 empty] | IOC
Sub-activity IV.2.2.2: Post-TWAP Strategy for Sustaining Periodic Assessment | [24 empty] | X | IOC | bar: 2014 I to 2014 VII
Sub-component IV.3: Assessment Coordination
Activity IV.3.1: Communication and Information Dissemination |  |  |  | X | [21 empty] | IOC
Activity IV.3.2: Data and information management system | [25 empty] | IOC | bar: IX to 2014 VII
Activity IV.3.3: Sub-project Coordination | [25 empty] | IOC
* Delivery of outputs (interim) x Delivery of outputs (final)
Component V: A Global Baseline Assessment of Open Ocean
Sub-component V.1: Assessment of Open Ocean
Activity V.1.1: Assembly of metrics and indices by theme
Sub-activity 1: Climate indices | [25 empty] | WCRP | bar: IX to 2014 VI
Sub-activity 2: Ecosystem indices | [25 empty] | PML | bar: IX to 2014 VI
Sub-activity 3: Fisheries indices | [25 empty] | UBC | bar: IX to 2014 VI
Sub-activity 4: Socioeconomic indices | [25 empty] | PCU/consultant | bar: IX to 2014 VI
Sub-activity 5: Cumulative mapping/OHI | [25 empty] | CMAP | bar: IX to 2014 VI
Sub-activity 6: Data and info management and interactive display system | [25 empty] | IOC/GEOWOW | bar: IX to 2014 VI
Activity V.1.2: Expert assessment by theme
Sub-activity 1: Climate assessment | [21 empty] | X |  |  |  | IOC/WCRP | bar: IX to 2014 VII
Sub-activity 2: Ecosystems assessment | [21 empty] | X |  |  |  | IOC | bar: IX to 2014 VII
Sub-activity 3: Fisheries assessment | [25 empty] | UBC | bar: IX to 2014 VI
Sub-activity 4: Pollution assessment | [21 empty] | X |  |  |  | GESAMP | bar: IX to 2014 VII
Sub-activity 5: Governance assessment | [21 empty] | X |  |  |  | Cermes | bar: IX to 2014 VII
Activity V.1.3: Assessment report and communication
Sub-activity 1: Report and communication | [24 empty] | X | IOC | bar: 2014 I to 2014 VII
Sub-component V.2: Framework for periodic OO assessment
Activity V.2.1: Establishment of a consortium of partners
Sub-activity 1: Working group coordination (meetings) |  |  | X | [22 empty] | IOC | bar: IX to 2014 VII
Activity V.2.2: Development of a strategy for linking TWAP with the ongoing UN Regular Process
Sub-activity 1: Engagement with RP and strategy for sustaining periodic assessment | [24 empty] | X | IOC
Sub-component V.3: Assessment Coordination
Activity V.3.1: Assessment coordination | [25 empty] | IOC
* Delivery of outputs (interim) x Delivery of outputs (final)
Component VI: Cross-cutting Issues Assessment
Sub-component VI.1: Governance assessment
Activity VI.1.1: Assess governance arrangements
Sub-activity 1: Establish/coordinate correspondence WG | [25 empty] | PCU/consultant
Sub-activity 2: Support WG collection of governance data | [25 empty] | PCU/consultant | bar: IX to XII
Sub-activity 3: Support WG governance analysis | [25 empty] | PCU/consultant | bar: XI to 2014 VI
Sub-activity 4: Select linked water systems | [25 empty] | PCU/consultant
Sub-activity 5: Acquire governance data on linked systems | [25 empty] | PCU/consultant | bar: IX to 2014 III
Sub-activity 6: Analyse governance data on linked systems | [25 empty] | PCU/consultant | bar: 2014 I to 2014 VII
Sub-activity 7: Revise governance architecture methodology | [20 empty] | X |  |  |  |  | PCU/consultant | bar: 2014 VII
Sub-activity 8: Cross-cutting governance assessment report | [20 empty] | X |  |  |  |  | PCU/consultant | bar: IX; 2014 VII
Sub-component VI.2: Socioeconomic issue assessment
Activity VI.2.1: Assessment of crosscutting social and economic features of human populations dependent on transboundary waters
Sub-activity 1:Establishment of a Crosscutting Socioeconomics Correspondence Group | [25 empty] | PCU/consultant
Sub-activity 2: Identification of input data products | [25 empty] | PCU/consultant
Sub-activity 3: Identification of core crosscutting socioeconomic indicators | [25 empty] | PCU/consultant
Sub-activity 4: Assessment of core crosscutting socioeconomic indicators for baseline conditions | [20 empty] | X |  |  |  |  | PCU/consultant | bar: IX to 2014 VII
Sub-activity 5: Assessment of core crosscutting socioeconomic indicators for projected scenarios | [20 empty] | X |  |  |  |  | PCU/consultant | bar: IX to 2014 VII
Sub-activity 6: Crosscutting Socioeconomics Assessment Report | [20 empty] | X |  |  |  |  | PCU/consultant | bar: IX; 2014 V to 2014 VII
Sub-component VI.3: Other cross cutting/common issue assessments
Activity VI.3.1: Assessment of selected crosscutting/common issues
Sub-activity 1: Identification and assessment of selected issues | [20 empty] | X |  |  |  |  | PCU/consultants | bar: IX to 2014 VII
X Delivery of outputs
Component VII: Data and Information Management
Sub-component VII.1 - Data and Information management system | [25 empty] | UNEP/DEWA
Activity VII.1.1: Data and Information Management Platform | [25 empty] | UNEP/DEWA
Sub-activity 1: Define a consolidated strategy for managing TWAP data and information | [25 empty] | UNEP/DEWA | bar: IX
Sub-activity 2: Review and harmonize data standards to facilitate data sharing | [25 empty] | UNEP/DEWA
Sub-activity 3: Build, upgrade and integrate TWAP Data Platform/Portal | [25 empty] | UNEP/DEWA
Sub-activity 4: Development of additional technical functionalities and services | [25 empty] | UNEP/DEWA
Sub-activity 5: Ensure compatibility with other relevant data and information systems | [25 empty] | UNEP/DEWA | bar: IX; 2014 V to 2014 VII
Activity VII.1.2: Project website - Interactions with IW:LEARN | [25 empty] | UNEP/DEWA
Sub-activity 1: Development of project website | [25 empty] | UNEP/DEWA
Sub-activity 2: Training and technical support | [25 empty] | UNEP/DEWA
Sub-activity 3: Ensure compatibility and linking of TWAP Data Portal and IW:learn | [25 empty] | UNEP/DEWA | bar: 2014 V to 2014 VII
Sub-activity 4: Content development for TWAP Project website | [25 empty] | UNEP/DEWA
Sub-component VII.2 - Assessment reporting - communication and outreach | [25 empty] | UNEP/DEWA
Activity VII.2.1 Publication and outreach | [25 empty] | UNEP/DEWA
Sub-activity 1: Publication of reports | [25 empty] | UNEP/DEWA | bar: 2014 VI to 2014 VII
Sub-activity 2: Preparation of outreach material | [25 empty] | UNEP/DEWA
Sub-activity 3: Communication and launches | [25 empty] | UNEP/DEWA
Component VIII: Terminal evaluation (TE)
Sub-component VIII.1: Terminal evaluation
Activity VIII.1.1: Terminal evaluation | [25 empty] | Evaluation and Oversight Unit of UNEP
Component IX: Project Management
Sub-component IX.1: Day-to-day Project Management (through the PCU including a Project Manager, a Technical Assistant, a Financial and Administrative Assistant from DEWA staff and consultants)
Activity IX.1.1: Networking and communication on substantive matters with partner agencies | [25 empty] | PCU
Activity IX.1.2: Preparation and processing of contracts and agreements | [25 empty] | PCU
Activity IX.1.3: PSC and STAP meetings
Sub-activity 1: PCU participation and support to PSC | [25 empty] | PCU | bar: XII
Sub-activity 2: STAC meetings (virtual, as part of PSC, or called upon by Components) | [25 empty] | PCU | bar: XII; 2014 IV
Activity IX.1.4: Financial and substantive reporting
Sub-activity 1: Reporting to UNEP and GEF (inception report, QERs, QORs, PIRs & Mid-term Management Review, etc.) | [6 empty] | o | [18 empty] | PCU | bar: IX; XII; 2014 III; 2014 VI
o PIR x Mid-term Management Review
Note on K164: SH:interim results